## RACI Matrix
Stakeholders / Project Roles
|  |  | Business Analyst | Field Rep | Sales Administrator | Sales Manager | IT Manager | CRM Software Developer | Website Developer | Company Executicves
| Actions / Tasks ¦ | Project Planning | R,A |  |  | C | C |  |  | I
|  | Elicit/ Analyze Requirements | R,A | C | C | C |  |  |  | I
|  | Solution Design | R,A |  |  |  | I | C | C
|  | Solution Design Approval | C | C | C | R,A | I | C | C | I
|  | CRM Changes | I |  |  |  | A | R
|  | Website Changes | I |  |  |  | A |  | R
|  | Test Solution | R,A | C | C | C | I | I | I | I
|  | Final Solution Approval | I | C | C | R,A |  |  |  | I
Template provided courtesy of The BA Guide
www.TheBAGuide.com