## Project
Project: Build a Road
The Inputs
Bill of Quantities BOQ
Activity Description | Quantity | Unit
Backfilling | 500 | m3
Asphalt | 100 | m2
Road Signs | 25 | pcs
Road Painting | 100 | m2
Project Duration: 12 Months. The company produce asphalt at a cost of 200$ per m2. A previous similar project that was 90 m2 of Asphalt was completed with a cost of 125,000$. Another project was completed with a cost of 500$ for each m2 of Asphalt. The team that will do the asphalt need special training.
After 6 months of working, we have the following information: - Backfilling Progress: 20%, Actual Cost: 12,000$ - Asphalt Progress: 5%, Actual Cost: 5,000$ - No work yet in the signs and painting
The Task is to Determine Budget and to check the performance.

## Budget
1. Driect and Indirect Costs
| Bill of Quantities BOQ |  |  |  |  | Reserves |  |  | Basis of Estimate | Three - point Estimating
| Activity Description | Quantity | Unit | Unit Cost | Total Cost | Contingency Reserves | Amount | Documentation |  | Co | Cp | Cm | Tri. Dist. | Peta. Dist.
| Direct |  |  |  | 0
WP | Backfilling | 500 | m3 | 148 | 74000 | 10% | 7400 | A risk that the backfilling may not comply with the quality. | Brainstorming meeting n#2 with Customer | 100 | 250 | 135 | 161.6667 | 148.3333
WP | Asphalt | 100 | m2 | 550 | 55000 |  |  |  | Parametric Estimating
| Asphalt Material | 100 | m2 | 200 | 20000
| Asphalt Pavement | 100 | m2 | 350 | 35000 | 15% | 5250 | A risk of rain in the execution period. | From Supplyer Bid
WP | Road Signs | 25 | pcs | 200 | 5000 | 5% | 250 | The price of signs may increase | Quotation from Supplyer
WP | Road Painting | 100 | m2 | 50 | 5000
WP | Indirect |  |  |  | 0
| Training for Asphalt Team | 1 | LS | 1000 | 1000 |  |  |  | Cost of Quality, from Quality Manager
| Survey Crew | 12 | month | 5000 | 60000 | 20% | 12000 | The hight turnover of the employees
| Management Crew | 12 | month | 5000 | 60000 | 20% | 12000 | The hight turnover of the employees
| Mobilization/Demobilization | 2 | Lumpsum | 1000 | 2000
| Offices + Furniture | 12 | month | 2000 | 24000
| Other Operations | 12 | month | 1000 | 12000
|  |  | Total |  | 298000 |  | 36900
|  |  | Total Cost & Reserves |  |  |  | 334900
[6 empty] | Management Reserve (10%) | 33490
| Analogous Estimating |  | Prev. Project |  | 125000
| Work Package Cost Estimate | 298000
| Contingency Reserves | 36900
| Management Reserve (10%) | 33490
| Cost Baseline | 334900
| Project Budget | 368390
| Day | Complete Process | Cost
| 2023-10-01 | 2% | 6698
| 2023-11-01 | 6% | 20094
| 2023-12-01 | 10% | 33490
| 2024-01-01 | 18% | 60282
| 2024-02-01 | 22% | 73678
| 2024-03-01 | 23% | 77027
| 2024-04-01 | 36% | 120564
| 2024-05-01 | 42% | 140658
| 2024-06-01 | 59% | 197591
| 2024-07-01 | 76% | 254524
| 2024-08-01 | 92% | 308108
| 2024-09-01 | 100% | 334900
Funding Requirement
[5 empty] | 2023-10-01 | 100000
[5 empty] | 2024-04-01 | 100000
[5 empty] | 2024-06-01 | 168390

## Performance
[5 empty] | Reserves |  | Cost Basline | After six months
Activity Description | Quantity | Unit | Unit Cost | Total Cost | Contingency Reserves | Amount |  | Progress | Actual Cost | Earned Value | CPI | CV | Status
Direct |  |  |  | 0
Backfilling | 500 | m3 | 148 | 74000 | 10% | 7400 | 81400 | 20% | 12000 | 16280 | 1.3567 | 4280 | Under Budget
Asphalt | 100 | m2 | 550 | 55000 |  |  | 60250 | 5% | 5000 | 3012.5 | 0.6025 | -1987.5 | Over Budget
Asphalt Material | 100 | m2 | 200 | 20000 |  |  | 20000
Asphalt Pavement | 100 | m2 | 350 | 35000 | 15% | 5250 | 40250
Road Signs | 25 | pcs | 200 | 5000 | 5% | 250 | 5250
Road Painting | 100 | m2 | 50 | 5000 |  |  | 5000
Indirect |  |  |  | 0
Training for Asphalt Team | 1 | LS | 1000 | 1000 |  |  | 1000 | 100% | 1000 | 1000 | 1 | 0 | On Budget
Survey Crew | 12 | month | 5000 | 60000 | 20% | 12000 | 72000 | 50% | 30000 | 36000 | 1.2 | 6000 | Under Budget
Management Crew | 12 | month | 5000 | 60000 | 20% | 12000 | 72000 | 50% | 30000 | 36000 | 1.2 | 6000 | Under Budget
Mobilization/Demobilization | 2 | Lumpsum | 1000 | 2000 |  |  | 2000 | 50% | 1000 | 1000 | 1 | 0 | On Budget
Offices + Furniture | 12 | month | 2000 | 24000 |  |  | 24000 | 50% | 12000 | 12000 | 1 | 0 | On Budget
Other Operations | 12 | month | 1000 | 12000 |  |  | 12000 | 50% | 6000 | 6000 | 1 | 0 | On Budget
[8 empty] | Total | 97000 | 111292.5 | 1.1473 | 14292.5 | Under Budget
Cost Baseline | 334900 | = BAC
Project Budget | 368390
Forecasting
Estimate Index |  |  |  |  | CPI for the previous work | 1.1
CPI | EV/AC |  |  |  | Scenario | CPI for the Remaining work | BAC - EV | ETC | EAC | VAC
SPI | EV/PV |  |  |  | 1 | 1 | 223607.5 | 223607.5 | 320607.5 | 14292.5
CV | EV-AC |  |  |  | 2 | 1.1 | 223607.5 | 203279.5455 | 300279.5455 | 34620.4545
SV | EV-PV |  |  |  | 3
[5 empty] | To-Complete Performance Index |  | (EAC = BAC)
[5 empty] | Remaining Money | Budget of Remaining Work | TCPI
[5 empty] | EAC - AC (1) | BAC - EV (2) | (2)/(1)
[5 empty] | 237900 | 223607.5 | 0.93992